## User Story Without Priority
LIST OF USER STORIES
S.N. | User Story | Acceptance Criteria
1 | As a new user, I want to create an account so that I can access library services. | • Add a register button in the navigation bar of the system. • Display the registration form when the button is clicked. • Provide all required fields (name, email, password) with proper validation. • Click the register button in the form to create the account. • Display a success message once registration is completed. • Show an error message if the email already exists in the system. • Securely store the password in the database after submission.
2 | As a user, I want to log in securely so that I can access my dashboard. | • Add a login button in the navigation bar of the system. • Display the login form when the button is clicked. • Enter valid credentials in the required fields with validation. • Click the login button to access the system. • Display an error message if credentials are incorrect. • Create a session upon successful authentication. • Redirect the user to the dashboard after successful login.
3 | As a user, I want to reset my password if forgotten. | • Add a “Forgot Password” option on the login page. • Click the option to open the password reset form. • Enter a registered email address and submit the form. • Send a password reset link to the provided email. • Open the reset link from the email. • Enter a new password in the reset form with validation. • Click the submit button to update the password successfully. • Show confirmation once password reset is completed.
4 | As a user, I want to log out securely after use. | • Add a logout button in the navigation bar or profile section. • Click the logout button to initiate the process. • Destroy the active user session upon logout. • Redirect the user to the login page after logout. • Block access to protected pages after session termination. • Show confirmation that the user has been successfully logged out.
5 | As a student, I want to browse all books so that I can choose what to borrow. | • Open the catalog page after accessing the system. • Display all available books when the page loads. • Show book details including title, author, and genre. • Indicate unavailable or out-of-stock books clearly. • Ensure the catalog loads quickly and efficiently.
6 | As a student, I want to search for books by title or author. | • Add a search bar in the navigation section of the system. • Enter keywords such as title, author, or genre. • Click the search button to trigger the search process. • Display matching books based on the search input. • Show partial matches for incomplete input. • Display a “No results found” message if no match exists. • Ensure results appear instantly after search execution.
7 | As a student, I want to filter books by category so that I find relevant books. | • Display all available genres when the page loads. • Allow the user to select one or multiple genres. • Update the book list based on selected filters. • Combine multiple filters for refined results. • Clear filters to restore the full book list.
8 | As a student, I want to see full book details before borrowing. | • Select a book from the catalog or search results. • Open the detailed book page. • Display complete information including title, author, ISBN, and availability. • Show stock/availability status clearly. • Provide a borrow button if the book is available.
9 | As a student, I want to borrow available books for reading. | • Select an available book from the catalog. • Click the borrow button to request the book. • Process the borrowing request and generate a due date. • Store the borrowing record in the database. • Show confirmation after successful borrowing.
10 | As a student, I want to return borrowed books. | • Open the list of borrowed books. • Click the return button for a selected book. • Process the return request and update stock. • Update the borrowing record in the database. • Display confirmation after successful return.
11 | As a student, I want to renew books if needed. | • Select a borrowed book before or on the due date. • Click the renewal option to extend due date. • Validate renewal eligibility and limits. • Extend the due date if conditions are met. • Save updated renewal information in the system.
12 | As a student, I want to view my history of borrowing. | • Log in and open the history section. • Display all borrowed and returned books. • Sort history by most recent activity. • Allow searching and filtering within history.
13 | As an admin, I want overdue fines calculated automatically. | • System checks overdue books automatically after due date. • Apply daily fine rate for overdue books. • Calculate total fine amount for each user. • Display updated fine in the system dashboard.
14 | As a student, I want to view unpaid fines. | • Open the user dashboard. • Display total outstanding fines clearly. • Show payment status (paid/unpaid). • Link fines with corresponding borrowed books. • Update status after successful payment.
15 | As a student, I want reminders before the due date. | • System checks upcoming due dates automatically. • Send reminder notifications before due date. • Deliver email reminders to users. • Include book details and due date in the message.
16 | As an admin, I want alerts for overdue books. | • System checks for overdue books regularly. • Generate alerts for overdue items. • Display overdue book list with user details. • Notify user or admin about overdue status.
17 | As an admin, I want to manage book inventory so that all library records remain accurate and updated. | • Access admin panel to manage books. • Add new books to the catalog. • Edit existing book details. • Delete books from the system. • Save changes and update catalog instantly.
18 | As a student, I want to view upcoming books so that I know which books will be available soon. | • Open the future books section. • Display upcoming book releases. • Show title, author, and release date. • Sort books by nearest release date. • Update list when admin modifies entries.
19 | As an admin, I want to activate or block accounts. | • Open user management panel. • Display all registered users. • Change user status (active/blocked). • Blocked users cannot log in. • Log all admin actions for tracking.
20 | As an admin, I want reports on library activities. | • Open system dashboard after login. • Display total books and issued books. • Show overdue book statistics. • Provide export option for reports. • Download system reports in file format.

## Agile User Story
AGILE USER STORY
Feature ID | Feature Name | User Story ID | Priority | As a <User> | I need to <task> | So that I can <goal> | Acceptance Criteria
F1 | User Account | 1.1 | High | User | User Registration | access the system | • Add register button in the navigation bar of the system. • Display the registration form when the button is clicked. • Provide all required fields with proper validation (name, email, password). • Click the register button to create the account successfully. • Show success message after successful registration.
|  | 1.2 | High | User | User Login | access my dashboard | • Add login button in the navigation bar of the system. • Display login form when the button is clicked. • Enter valid login credentials in required fields. • Click login button to access the system. • Redirect to dashboard after successful login.
|  | 1.3 | Medium | User | Forgot Password | recover my account | • Add forgot password option on login page. • Click forgot password button. • Enter registered email in the reset form. • Send password reset link to email. • Open reset link to set new password. • Reset link expires after 24 hours.
|  | 1.4 | Low | User | Logout | secure my account | • Add logout button in the system dashboard. • Click logout button to end session. • Destroy user session after logout. • Redirect user to login page. • Block access to dashboard after logout.
F2 | Book Catalog | 2.1 | High | User | View Book Catalog | browse available books | • Display all books in catalog page. • Show book title, author, and genre. • Show availability status of each book. • Load catalog page efficiently.
|  | 2.2 | High | User | Search Books | find books quickly | • Add search bar in catalog page. • Allow search by book title or author. • Show matching results instantly. • Display “no results found” message if empty.
|  | 2.3 | Medium | User | Filter by Genre | find relevant books | • Show all available genres from database. • Allow selection of one or multiple genres. • Update book list based on selected filter. • Provide clear filter option.
|  | 2.4 | High | User | View Book Details | understand book information | • Open detailed page when book is selected. • Display title, author, ISBN, and description. • Show availability and quantity. • Display borrow button on details page.
F3 | Borrowing System | 3.1 | High | User | Borrow Book | read books | • Allow borrowing only available books. • Generate due date automatically after borrowing. • Store borrow record in database. • Show confirmation message after borrowing.
|  | 3.2 | High | Admin | Return Book | return borrowed items | • Provide return option for borrowed books. • Update stock after return. • Update borrow record status. • Show return confirmation message.
|  | 3.3 | Medium | Admin | Renew Book | extend borrowing period | • Allow renewal before due date. • Generate new due date after renewal. • Restrict renewal after limit is reached. • Save updated record in system.
|  | 3.4 | Medium | Admin | Borrow History | track my activity | • Display list of borrowed books. • Show returned and active borrow records. • Sort history by latest activity. • Allow search within history.
F4 | Fine Management | 4.1 | High | Admin | Fine Calculation | ensure penalties are applied | • Calculate fine after due date expires. • Apply daily fine rate automatically. • Display total fine amount clearly. • Update fine in real time.
|  | 4.2 | Medium | User | Fine Payment Status | check my fines | • Display unpaid fines in dashboard. • Show paid and unpaid status clearly. • Link fines to respective books. • Update status after payment.
|  | 4.3 | Low | User | Due Date Reminder | avoid late returns | • Send reminder before due date. • Include book details in notification. • Send email notification to user. • Display due date clearly in message.
|  | 4.4 | Medium | Admin | Overdue Alert | manage overdue books | • Detect overdue books automatically. • Display overdue list in admin panel. • Show user details with overdue books. • Allow admin to notify users.
F5 | Admin Management | 5.1 | High | Admin | Book Inventory Management | maintain accurate records | • Add new books to system. • Edit existing book details. • Delete removed or damaged books. • Update catalog instantly after changes.
|  | 5.2 | High | Admin | Manage Users | control user access | • Display list of all users. • Allow activation and blocking of users. • Prevent blocked users from logging in. • Log all admin actions.
|  | 5.3 | High | Admin | Reports Dashboard | analyze system performance | • Display total number of books. • Show issued and returned book statistics. • Display overdue book records. • Allow export of reports in file format.
F6 | Additional Features | 6.1 | Low | User | Future Releases | know upcoming books | • Display upcoming books section. • Show title, author, and release date. • Sort books by nearest release date. • Allow admin to update future releases.

## User Story Priority Hierarcy
AGILE USER STORY - HIERARCHY
Feature ID | User Story Id | Priority | As a <Type of user> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19
F1 | 1.1 | High | User | User Registration | access the system | • Add register button in the navigation bar of the system. • Display the registration form when the button is clicked. • Provide all required fields with proper validation (name, email, password). • Click the register button to create the account successfully. • Show success message after successful registration.
F1 | 1.2 | High | User | User Login | access my dashboard | • Add login button in the navigation bar of the system. • Display login form when the button is clicked. • Enter valid login credentials in required fields. • Click login button to access the system. • Redirect to dashboard after successful login.
F2 | 2.1 | High | User | View Book Catalog | browse available books | • Display all books in catalog page. • Show book title, author, and genre. • Show availability status of each book. • Load catalog page efficiently.
F2 | 2.2 | High | User | Search Books | find books quickly | • Add search bar in catalog page. • Allow search by book title or author. • Show matching results instantly. • Display “no results found” message if empty.
F2 | 2.4 | High | User | View Book Details | understand book information | • Open detailed page when book is selected. • Display title, author, ISBN, and description. • Show availability and quantity. • Display borrow button on details page.
F3 | 3.1 | High | User | Borrow Book | read books | • Allow borrowing only available books. • Generate due date automatically after borrowing. • Store borrow record in database. • Show confirmation message after borrowing.
F3 | 3.2 | High | Admin | Return Book | return borrowed items | • Provide return option for borrowed books. • Update stock after return. • Update borrow record status. • Show return confirmation message.
F4 | 4.1 | High | Admin | Fine Calculation | ensure penalties are applied | • Calculate fine after due date expires. • Apply daily fine rate automatically. • Display total fine amount clearly. • Update fine in real time.
F5 | 5.1 | High | Admin | Book Inventory Management | maintain accurate records | • Add new books to system. • Edit existing book details. • Delete removed or damaged books. • Update catalog instantly after changes.
F5 | 5.2 | High | Admin | Manage Users | control user access | • Display list of all users. • Allow activation and blocking of users. • Prevent blocked users from logging in. • Log all admin actions.
F5 | 5.3 | High | Admin | Reports Dashboard | analyze system performance | • Display total number of books. • Show issued and returned book statistics. • Display overdue book records. • Allow export of reports in file format.
F1 | 1.3 | Medium | User | Forgot Password | recover my account | • Add forgot password option on login page. • Click forgot password button. • Enter registered email in the reset form. • Send password reset link to email. • Open reset link to set new password. • Reset link expires after 24 hours.
F2 | 2.3 | Medium | User | Filter by Genre | find relevant books | • Show all available genres from database. • Allow selection of one or multiple genres. • Update book list based on selected filter. • Provide clear filter option.
F3 | 3.3 | Medium | Admin | Renew Book | extend borrowing period | • Allow renewal before due date. • Generate new due date after renewal. • Restrict renewal after limit is reached. • Save updated record in system.
F3 | 3.4 | Medium | Admin | Borrow History | track my activity | • Display list of borrowed books. • Show returned and active borrow records. • Sort history by latest activity. • Allow search within history.
F4 | 4.2 | Medium | User | Fine Payment Status | check my fines | • Display unpaid fines in dashboard. • Show paid and unpaid status clearly. • Link fines to respective books. • Update status after payment.
F4 | 4.4 | Medium | Admin | Overdue Alert | manage overdue books | • Detect overdue books automatically. • Display overdue list in admin panel. • Show user details with overdue books. • Allow admin to notify users.
F1 | 1.4 | Low | User | Logout | secure my account | • Add logout button in the system dashboard. • Click logout button to end session. • Destroy user session after logout. • Redirect user to login page. • Block access to dashboard after logout.
F4 | 4.3 | Low | User | Due Date Reminder | avoid late returns | • Send reminder before due date. • Include book details in notification. • Send email notification to user. • Display due date clearly in message.
F6 | 6.1 | Low | User | Future Releases | know upcoming books | • Display upcoming books section. • Show title, author, and release date. • Sort books by nearest release date. • Allow admin to update future releases.

## User Story Map Board
Legend : US - User Story
The Backbone | User Account | Book Catalog | Borrowing System | Fine Management | Admin Management
Flesh on the backbone | Authentication | Book Browsing | Borrowing Process | Fine Handling | System Administration
Sprint / Iteration 1 (17/05/2026 - 22/05/2026) | US 1 – User Registration
SEQUENCE |  | US 5 – View Book Catalog
Version 1.0 |  |  | US 9 – Borrow Book |  | US 17 – Book Inventory Management
Sprint / Iteration 2 (24/05/2026 - 29/05/2026)
Version 2.0 | US 2 – User Login | US 6 – Search Books | US 10 – Return Book
US 8 – View Book Details
Sprint / Iteration 3 (31/06/2026 - 05/06/2026)
Version 3.0
| US 3 – Forgot Password | US 7 – Filter by Genre | US 11 – Renew Book
US 12 – Borrow History
Sprint / Iteration 4 (07/06/2026 - 12/05/2026) |  |  |  | US 13 – Fine Calculation
Version 4.0 |  |  |  | US 14 – Fine Payment Status
US 15 – Due Date Reminder
| US 4 – Logout |  |  | US 16 – Overdue Alert
Sprint / Iteration 5 (14/06/2026 - 19/06/2026)
Version 5.0 |  |  |  |  | US 18 – Manage Users
US 19 – Reports Dashboard
US 20 – Future Releases

## Agile Realese Plan
AGILE REALESE PLAN
AT RISK | SPRINT | USER STORY NAME | FEATURE TYPE | START | FINISH | DURATION (In Hours) | STORY POINTS | STATUS | RELEASE DATE
| 1 | User Story 1 – User Registration | User Account | 17/05/2026 | 22/05/2026 | 2 | 1.5 | Completed | 22/05/2026
| 1 | User Story 5 – View Book Catalog | Book Catalog | 17/05/2026 | 22/05/2026 | 4 | 1 | Completed | 22/05/2026
| 1 | User Story 9 – Borrow Book | Borrowing System | 17/05/2026 | 22/05/2026 | 4 | 1.5 | Completed | 22/05/2026
| 1 | User Story 17 – Book Inventory Management | Admin Management | 17/05/2026 | 22/05/2026 | 4 | 1.5 | Completed | 22/05/2026 | User Story 2 – User Login
| 2 | User Story 2 – User Login | User Account | 24/05/2026 | 29/05/2026 | 3 | 1 | Completed | 29/05/2026 | User Story 3 – Forgot Password
| 2 | User Story 6 – Search Books | Book Catalog | 24/05/2026 | 29/05/2026 | 3 | 1 | Completed | 29/05/2026 | User Story 4 – Logout
| 2 | User Story 10 – Return Book | Borrowing System | 24/05/2026 | 29/05/2026 | 3 | 1 | Completed | 29/05/2026
| 2 | User Story 8 – View Book Details | Book Catalog | 24/05/2026 | 29/05/2026 | 2 | 0.5 | Completed | 29/05/2026 | User Story 6 – Search Books
| 3 | User Story 3 – Forgot Password | User Account | 31/05/2026 | 05/06/2026 | 4 | 1.5 | Completed | 05/06/2026 | User Story 7 – Filter by Genre
| 3 | User Story 7 – Filter by Genre | Book Catalog | 31/05/2026 | 05/06/2026 | 3 | 1 | Completed | 05/06/2026 | User Story 8 – View Book Details
| 3 | User Story 11 – Renew Book | Borrowing System | 31/05/2026 | 05/06/2026 | 3 | 1 | Completed | 05/06/2026
| 3 | User Story 12 – Borrow History | Borrowing System | 31/05/2026 | 05/06/2026 | 3 | 1 | Completed | 05/06/2026 | User Story 10 – Return Book
| 4 | User Story 13 – Fine Calculation | Fine Management | 07/06/2026 | 12/06/2026 | 3 | 1 | Completed | 12/06/2026 | User Story 11 – Renew Book
| 4 | User Story 14 – Fine Payment Status | Fine Management | 07/06/2026 | 12/06/2026 | 3 | 1 | Completed | 12/06/2026 | User Story 12 – Borrow History
| 4 | User Story 15 – Due Date Reminder | Fine Management | 07/06/2026 | 12/06/2026 | 4 | 1.5 | Completed | 12/06/2026
| 4 | User Story 16 – Overdue Alert | Fine Management | 07/06/2026 | 12/06/2026 | 3 | 1 | Completed | 12/06/2026 | User Story 14 – Fine Payment Status
| 5 | User Story 4 – Logout | User Account | 14/06/2026 | 19/06/2026 | 2 | 0.5 | Completed | 19/06/2026 | User Story 15 – Due Date Reminder
| 5 | User Story 18 – Manage Users | Admin Management | 14/06/2026 | 19/06/2026 | 3 | 1 | Completed | 19/06/2026 | User Story 16 – Overdue Alert
| 5 | User Story 19 – Reports Dashboard | Admin Management | 14/06/2026 | 19/06/2026 | 4 | 1.5 | Completed | 19/06/2026
| 5 | User Story 20 – Future Releases | Additional Features | 14/06/2026 | 19/06/2026 | 2 | 0.5 | Completed | 19/06/2026 | User Story 18 – Manage Users
User Story 19 – Reports Dashboard
User Story 20 – Future Releases

## Agile Sprint 1 Backlog
AGILE SPRINT 1 BACKLOG | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 : User Registration | 1.5 | Aadhar SJB Rana | Completed | 2 | 0.5 | 1 | 0 | 0.5 | 0 | Completed
Frontend | Column2: Aadhar SJB Rana; Column3: Completed
Backend | Column2: Aadhar SJB Rana; Column3: Completed
Database | Column2: Aadhar SJB Rana; Column3: Completed
Testing | Column2: Aadhar SJB Rana; Column3: Completed
Validation | Column2: Aadhar SJB Rana; Column3: Completed
User Story #5 – View Book Catalog | 1 | Aman Man Shrestha | Completed | 4 | 0.5 | 0.5 | 1 | 1 | 1 | Completed
Frontend | Column2: Aman Man Shrestha; Column3: Completed
Backend | Column2: Aman Man Shrestha; Column3: Completed
Database | Column2: Aman Man Shrestha; Column3: Completed
Testing | Column2: Aman Man Shrestha; Column3: Completed
Validation | Column2: Aman Man Shrestha; Column3: Completed
User Story #9 – Borrow Book | 1.5 | Rashmi Deep Bhandari | Completed | 4 | 0.5 | 1 | 1 | 1 | 0.5 | Completed
Frontend | Column2: Rashmi Deep Bhandari; Column3: Completed
Backend | Column2: Rashmi Deep Bhandari; Column3: Completed
Database | Column2: Rashmi Deep Bhandari; Column3: Completed
Testing | Column2: Rashmi Deep Bhandari; Column3: Completed
Validation | Column2: Rashmi Deep Bhandari; Column3: Completed
User Story #13 – Fine Calculation | 1 | Kushal Basnet | Completed | 3 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | Completed
Frontend | Column2: Kushal Basnet; Column3: Completed
Backend | Column2: Kushal Basnet; Column3: Completed
Database | Column2: Kushal Basnet; Column3: Completed
Testing | Column2: Kushal Basnet; Column3: Completed
Validation | Column2: Kushal Basnet; Column3: Completed
User Story #17 – Book Inventory Management | 1.5 | Ronish Pant | Completed | 4 | 0.5 | 0.5 | 1 | 1 | 1 | Completed
Frontend | Column2: Ronish Pant; Column3: Completed
Backend | Column2: Ronish Pant; Column3: Completed
Database | Column2: Ronish Pant; Column3: Completed
Testing | Column2: Ronish Pant; Column3: Completed
Validation | Column2: Ronish Pant; Column3: Completed
Estimated | Column5: 14.5; Column6: 11; Column7: 7; Column8: 3; Column9: 0
Ideal | Column5: 13.6; Column6: 10.2; Column7: 6.8; Column8: 3.4; Column9: 0

## Agile Sprint 2 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #2 : User Login | 1 | Aadhar SJB Rana | Completed | 3 | 1 | 1 | 0.5 | 0.5 | 0 | Completed
Frontend |  | Aadhar SJB Rana | Completed
Backend |  | Aadhar SJB Rana | Completed
Database |  | Aadhar SJB Rana | Completed
Testing |  | Aadhar SJB Rana | Completed
Validation |  | Aadhar SJB Rana | Completed
User Story #6 – Search Books | 1 | Aman Man Shrestha | Completed | 3 | 0.5 | 1 | 1 | 0.5 | 0 | Completed
Frontend |  | Aman Man Shrestha | Completed
Backend |  | Aman Man Shrestha | Completed
Database |  | Aman Man Shrestha | Completed
Testing |  | Aman Man Shrestha | Completed
Validation |  | Aman Man Shrestha | Completed
User Story #10 – Return Book | 1 | Rashmi Deep Bhandari | Completed | 3 | 0.5 | 0.5 | 1 | 1 | 0 | Completed
Frontend |  | Rashmi Deep Bhandari | Completed
Backend |  | Rashmi Deep Bhandari | Completed
Database |  | Rashmi Deep Bhandari | Completed
Testing |  | Rashmi Deep Bhandari | Completed
Validation |  | Rashmi Deep Bhandari | Completed
User Story #14 – Fine Payment Status | 1 | Kushal Basnet | Completed | 3 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | Completed
Frontend |  | Kushal Basnet | Completed
Backend |  | Kushal Basnet | Completed
Database |  | Kushal Basnet | Completed
Testing |  | Kushal Basnet | Completed
Validation |  | Kushal Basnet | Completed
User Story #18 – Manage Users | 1 | Ronish Pant | Completed | 3 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | Completed
Frontend |  | Ronish Pant | Completed
Backend |  | Ronish Pant | Completed
Database |  | Ronish Pant | Completed
Testing |  | Ronish Pant | Completed
Validation |  | Ronish Pant | Completed
Estimated |  |  |  |  | 12 | 8.5 | 4.5 | 1 | 0
Ideal |  |  |  |  | 12 | 9 | 6 | 3 | 0

## Agike Sprint 3 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #3 : Forgot Password | 1.5 | Aadhar SJB Rana | Completed | 4 | 1 | 1 | 1 | 1 | 0 | Completed
Frontend |  | Aadhar SJB Rana | Completed
Backend |  | Aadhar SJB Rana | Completed
Database |  | Aadhar SJB Rana | Completed
Testing |  | Aadhar SJB Rana | Completed
Validation |  | Aadhar SJB Rana | Completed
User Story #7 – Filter by Genre | 1 | Aman Man Shrestha | Completed | 3 | 0.5 | 1 | 1 | 0.5 | 0 | Completed
Frontend |  | Aman Man Shrestha | Completed
Backend |  | Aman Man Shrestha | Completed
Database |  | Aman Man Shrestha | Completed
Testing |  | Aman Man Shrestha | Completed
Validation |  | Aman Man Shrestha | Completed
User Story #11 – Renew Book | 1 | Rashmi Deep Bhandari | Completed | 3 | 0.5 | 0.5 | 1 | 1 | 0 | Completed
Frontend |  | Rashmi Deep Bhandari | Completed
Backend |  | Rashmi Deep Bhandari | Completed
Database |  | Rashmi Deep Bhandari | Completed
Testing |  | Rashmi Deep Bhandari | Completed
Validation |  | Rashmi Deep Bhandari | Completed
User Story #15 – Due Date Reminder | 1.5 | Kushal Basnet | Completed | 4 | 0.5 | 1 | 1 | 1 | 0.5 | Completed
Frontend |  | Kushal Basnet | Completed
Backend |  | Kushal Basnet | Completed
Database |  | Kushal Basnet | Completed
Testing |  | Kushal Basnet | Completed
Validation |  | Kushal Basnet | Completed
User Story #19 – Reports Dashboard | 1.5 | Ronish Pant | Completed | 4 | 0.5 | 1 | 1 | 1 | 0.5 | Completed
Frontend |  | Ronish Pant | Completed
Backend |  | Ronish Pant | Completed
Database |  | Ronish Pant | Completed
Testing |  | Ronish Pant | Completed
Validation |  | Ronish Pant | Completed
Estimated |  |  |  |  | 15 | 10.5 | 5.5 | 1 | 0
Ideal |  |  |  |  | 14.4 | 10.8 | 7.2 | 3.6 | 0

## Agile Sprint 4 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #13 – Fine Calculation | 1 | Kushal Basnet | Completed | 3 | 1 | 1 | 1 | 0 | 0 | Completed
Frontend |  | Kushal Basnet | Completed
Backend |  | Kushal Basnet | Completed
Database |  | Kushal Basnet | Completed
Testing |  | Kushal Basnet | Completed
Validation |  | Kushal Basnet | Completed
User Story #14 – Fine Payment Status | 1 | Kushal Basnet | Completed | 3 | 0.5 | 1 | 1 | 0.5 | 0 | Completed
Frontend |  | Kushal Basnet | Completed
Backend |  | Kushal Basnet | Completed
Database |  | Kushal Basnet | Completed
Testing |  | Kushal Basnet | Completed
Validation |  | Kushal Basnet | Completed
User Story #15 – Due Date Reminder | 1.5 | Kushal Basnet | Completed | 4 | 1 | 1 | 1 | 1 | 0 | Completed
Frontend |  | Kushal Basnet | Completed
Backend |  | Kushal Basnet | Completed
Database |  | Kushal Basnet | Completed
Testing |  | Kushal Basnet | Completed
Validation |  | Kushal Basnet | Completed
User Story #16 – Overdue Alert | 1 | Kushal Basnet | Completed | 3 | 0.5 | 0.5 | 1 | 1 | 0 | Completed
Frontend |  | Kushal Basnet | Completed
Backend |  | Kushal Basnet | Completed
Database |  | Kushal Basnet | Completed
Testing |  | Kushal Basnet | Completed
Validation |  | Kushal Basnet | Completed
Estimated |  |  |  |  | 10 | 6.5 | 2.5 | 0 | 0
Ideal |  |  |  |  | 10.4 | 7.8 | 5.2 | 2.6 | 0

## Agile Sprint 5 Backlog
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #4 : Logout | 0.5 | Aadhar SJB Rana | Completed | 2 | 0.5 | 0.5 | 1 | 0 | 0 | Completed
Frontend |  | Aadhar SJB Rana | Completed
Backend |  | Aadhar SJB Rana | Completed
Database |  | Aadhar SJB Rana | Completed
Testing |  | Aadhar SJB Rana | Completed
Validation |  | Aadhar SJB Rana | Completed
User Story #8 – View Book Details | 0.5 | Aman Man Shrestha | Completed | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | Completed
Frontend |  | Aman Man Shrestha | Completed
Backend |  | Aman Man Shrestha | Completed
Database |  | Aman Man Shrestha | Completed
Testing |  | Aman Man Shrestha | Completed
Validation |  | Aman Man Shrestha | Completed
User Story #19 – Reports Dashboard | 1.5 | Ronish Pant | Completed | 4 | 1 | 1 | 1 | 1 | 0 | Completed
Frontend |  | Ronish Pant | Completed
Backend |  | Ronish Pant | Completed
Database |  | Ronish Pant | Completed
Testing |  | Ronish Pant | Completed
Validation |  | Ronish Pant | Completed
User Story #20 – Future Releases | 0.5 | Ronish Pant | Completed | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | Completed
Frontend |  | Ronish Pant | Completed
Backend |  | Ronish Pant | Completed
Database |  | Ronish Pant | Completed
Testing |  | Ronish Pant | Completed
Validation |  | Ronish Pant | Completed
Estimated |  |  |  |  | 7.5 | 5 | 2 | 0 | 0
Ideal |  |  |  |  | 8 | 6 | 4 | 2 | 0

## Attendance log
Attendance Log
Week 1
Name | Planning | Daily StandUp 1 | Daily StandUp2 | Daily StandUp 3 | Daily StandUp4 | Daily StandUp5 | Review | Retrospective | Total
Aadhar SJB Rana | Present | Present | Present | Present | Present | Present | Present | Present
Aman Man Shrestha | Present | Present | Present | Present | Present | Present | Present | Present
Rashmi Deep Bhandari | Present | Present | Present | Present | Present | Present | Present | Present
Ronish Pant | Present | Present | Present | Present | Present | Present | Present | Present
Kushal Basnet | Present | Present | Absent | Present | Present | Present | Present | Present
Week 2
Name | Planning | Daily StandUp1 | Daily StandUp2 | Daily StandUp3 | Daily StandUp4 | Daily StandUp5 | Review | Retrospective
Aadhar SJB Rana | Present | Present | Present | Present | Present | Present | Present | Present
Aman Man Shrestha | Present | Present | Present | Present | Present | Present | Present | Present
Rashmi Deep Bhandari | Present | Present | Present | Present | Present | Present | Present | Present
Ronish Pant | Present | Present | Absent | Absent | Present | Present | Present | Present
Kushal Basnet | Present | Present | Present | Present | Present | Present | Present | Present
Week 3
Name | Planning | Daily StandUp1 | Daily StandUp 2 | Daily StandUp 3 | Daily StandUp4 | Daily StandUp 5 | Review | Retrospective
Aadhar SJB Rana | Present | Present | Present | Present | Present | Present | Present | Present
Aman Man Shrestha | Present | Present | Present | Present | Present | Present | Present | Present
Rashmi Deep Bhandari | Present | Present | Present | Present | Present | Present | Present | Present
Ronish Pant | Present | Present | Present | Present | Present | Present | Present | Present
Kushal Basnet | Present | Present | Present | Present | Present | Present | Present | Present
Week 4
Name | Planning | Daily StandUp1 | Daily StandUp 2 | Daily StandUp 3 | Daily StandUp4 | Daily StandUp 5 | Review | Retrospective
Aadhar SJB Rana | Present
Aman Man Shrestha | Present
Rashmi Deep Bhandari | Absent
Ronish Pant | Present
Kushal Basnet | Present
Week 5
Name | Planning | Daily StandUp1 | Daily StandUp 2 | Daily StandUp 3 | Daily StandUp4 | Daily StandUp 5 | Review | Retrospective
Aadhar SJB Rana
Aman Man Shrestha
Rashmi Deep Bhandari
Ronish Pant
Kushal Basnet
Name | Total
Aadhar SJB Rana
Aman Man Shrestha
Rashmi Deep Bhandari
Ronish Pant
Kushal Basnet